TO: Tracy Alderson-Allen, Amy Allen, Chase Pierson FROM: Office of the CFO DATE: April 20, 2026 SUBJECT: Business Case & 12-Month Pro Forma: Big Muddy / MBT Ecosystem (FY 2026-2027)

This document outlines the business case and a 12-month operating pro forma for the consolidated Big Muddy and MBT ecosystem. The model targets $760,000 in total revenue for the period from Q2 2026 through Q1 2027. The projections herein are conservative and based on operational assumptions detailed in each section. The objective is to provide a clear, factual basis for strategic decisions and resource allocation over the next fiscal year.

### 1. Executive Summary

As of April 20, 2026, the foundational assets of the ecosystem are operational. The MBT technology platform is live, with the Sanity CMS and Vercel front-end deployment functioning as designed. The flagship implementation, Big Muddy, is active, with the Inn accepting guests, the Magazine publishing its initial content slate (10 articles), and Big Muddy Touring managing its first bookings. Deep South Directory (DSD) is ready for subscriber acquisition. This initial 12-month period is focused on validating the core business hypothesis: that a vertically integrated media and hospitality model can create a flywheel, where content drives high-margin hospitality revenue, and the surrounding business community is monetized through the DSD tech platform.

The “Lean & Mean” financial model targets $760,000 in gross revenue for the first year (Q2 2026 - Q1 2027). This target is ambitious but achievable if key performance indicators are met, primarily concerning Inn occupancy rates and the velocity of DSD subscriber acquisition. The primary risks to the model are executional: sales velocity for DSD, market-rate occupancy at the Inn, and the successful integration of programming (JP Houston) to drive consistent traffic to the Blues Room.

Key assets have been de-risked: the core technology stack is built, the physical Inn property is operational, and initial content and branding are in place. The aspirational elements remain the market’s response—specifically, the conversion rates for DSD and the booking velocity for the Inn and Touring arms. This pro forma serves as our operational map to transition those aspirational components into reliable, recurring revenue streams.

### 2. Revenue Model — By Brand

The following table projects monthly revenue by brand. Totals are rounded to the nearest dollar.

| Brand | Apr ’26 | May ’26 | Jun ’26 | Jul ’26 | Aug ’26 | Sep ’26 | Oct ’26 | Nov ’26 | Dec ’26 | Jan ’27 | Feb ’27 | Mar ’27 | Annual Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Big Muddy Inn | $14,400 | $18,000 | $21,600 | $25,200 | $21,600 | $28,800 | $32,400 | $27,000 | $21,600 | $18,000 | $18,000 | $21,600 | $268,800 |
| Big Muddy Magazine | $0 | $0 | $500 | $500 | $500 | $1,000 | $1,000 | $1,000 | $1,500 | $1,500 | $1,500 | $2,000 | $11,000 |
| Big Muddy Touring | $1,500 | $2,000 | $2,500 | $3,000 | $3,000 | $4,500 | $5,000 | $4,000 | $3,500 | $2,500 | $2,500 | $3,000 | $37,000 |
| Big Muddy Records | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 |
| Big Muddy Radio | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $500 | $750 | $1,000 | $1,250 | $3,500 |
| DSD | $575 | $1,250 | $2,125 | $3,250 | $4,575 | $6,200 | $8,175 | $10,400 | $12,925 | $15,700 | $18,775 | $22,150 | $106,100 |
| Tuthill Design | $2,000 | $2,000 | $3,000 | $3,000 | $2,000 | $4,000 | $4,000 | $3,000 | $5,000 | $3,000 | $2,000 | $4,000 | $37,000 |
| Studio C Video | $3,000 | $3,000 | $4,000 | $4,000 | $3,000 | $5,000 | $5,000 | $4,000 | $6,000 | $4,000 | $3,000 | $5,000 | $49,000 |
| Bearsville Creative | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $0 |
| Monthly Total | $21,475 | $26,250 | $33,725 | $38,950 | $34,675 | $49,500 | $55,575 | $49,400 | $51,025 | $45,450 | $46,775 | $58,000 | $510,800 |

Note on Revenue Target: The bottom-up pro forma totals $510,800. This is a conservative base case. Reaching the $760,000 “Lean & Mean” target requires outperformance in key areas, primarily a faster DSD ramp to Pro/Engine tiers and higher average occupancy/ADR at the Inn, plus successful booking of whole-Inn rentals and larger touring packages. The $249,200 gap represents the primary operational challenge and sales target for the leadership team.

Revenue Assumptions:

- Inn: Modeled on 6 rooms at a $200 blended Average Daily Rate (ADR). Occupancy ramps from 40% in shoulder months to 75% in peak season (Fall). Includes an estimated $2,400/mo from Blues Room ticket sales and bar revenue, assuming 4 shows/mo at 30 tickets avg.

- Magazine: Assumes no significant ad revenue in H1. Small sponsorships ($500-$2k/mo) begin in Q3 as traffic and brand recognition grow. Primary value is Inn conversion, not direct revenue.

- Touring: Based on a mix of booking fees ($500-$1k/show), a percentage of door sales from managed shows, and a margin on Sprinter van rentals to third-party acts. Ramps as network and reputation are established.

- Records/Radio: Pre-revenue for Year 1 as stated. Radio model includes launch of small sponsorship packages in late Q4/Q1.

- DSD: Assumes a consistent acquisition of 150 new free users per month (5/day). Models a 15% conversion rate to Essentials ($25/mo), a 2% conversion to Pro ($50/mo), and a 0.5% conversion to Marketing ($99/mo) on a rolling, cumulative basis. Assumes 2 Engine ($250/mo) clients are closed in H2.

- Tuthill / Studio C: Represents the MBT licensing fee and project management margin on work fulfilled by partners. Modeled as lumpy, project-based revenue.

- Bearsville: Zero revenue is modeled for FY 2026-27. Activation in Summer 2026 is for planning and setup; revenue is projected for FY 2027-28.

### 3. Cost Structure — Annual Run-Rate

| Category | Description | Annual Cost ($) |
| --- | --- | --- |
| Operating Costs |  |  |
| Inn Property | Mortgage, property tax, insurance for Natchez property. | $60,000 |
| Payroll & Compensation | Draws/salaries for C. Pierson, T. Alderson-Allen, A. Allen. Stipends/salary for JP Houston, Elijah, Miles. | $264,000 |
| Inn Operations | Linens, cleaning, supplies, breakfast COGS, bar stock COGS. | $36,000 |
| Utilities | Electricity, water, waste, high-speed internet (Inn + Office). | $18,000 |
| Platform Costs |  |  |
| Hosting & Services | Vercel, Sanity, Google Cloud Storage, AI APIs, Resend, etc. | $2,400 |
| Transaction Fees | Stripe fees (estimated at 3.0% of applicable revenue). | $15,324 |
| Touring Costs |  |  |
| Vehicle & Travel | Sprinter van lease/payment, insurance, maintenance, fuel. | $25,000 |
| Artist Guarantees | Guarantees for house band and booked acts (partially offset by ticket sales). | $50,000 |
| General & Admin |  |  |
| Marketing & Sales | Digital ads, print materials, travel for sales, promotional events. | $24,000 |
| Professional Services | Legal, accounting. | $10,000 |
| Subtotal: Operating Expenses |  | $504,724 |
| Reserves | 10% contingency for unforeseen expenses. | $50,472 |
| Total Annual Costs |  | $555,196 |

### 4. Margin & Cash Position

- Gross Margin:

  - Inn: High (~75%). Revenue less direct COGS (supplies, breakfast food, bar stock).

  - DSD: Very High (~95%). Revenue less platform/Stripe fees. The primary cost is payroll, which is an operating expense.

  - Touring: Low (~25%). Revenue less artist guarantees, fuel, and specific travel costs. Highly variable.

  - Media (Magazine/Radio): Very High (~90%). Revenue less transaction fees. Costs are OpEx.

- EBITDA Projection (Base Case):

  - Projected Annual Revenue: $510,800

  - Projected Annual Costs (ex-Reserves): $504,724

  - Projected EBITDA: $6,076

  - Note: This thin margin underscores the critical importance of hitting revenue targets. Reaching the $760k target would yield an EBITDA of approximately $255,276, demonstrating the model’s operating leverage.

- Cash Position:

  - Assuming a starting cash balance of $50,000 on April 1, 2026.

  - 6-Month Cash Position (Est. Sep 30, 2026): The first six months show a cumulative revenue of $214,575 against estimated cash outlays of ~$252,000 (50% of annual OpEx). This results in a projected cash burn of ~$37,425, for an ending balance of $12,575. This is the point of maximum financial risk.

  - 12-Month Cash Position (Est. Mar 31, 2027): With revenue accelerating in H2, the full-year projection shows a slight positive cash flow. Starting Cash ($50k) + Revenue ($510.8k) - Costs ($555.2k) results in a projected ending balance of $5,600. This highlights the lack of buffer and the need for strict cost control or faster-than-projected revenue growth.

- Bottlenecks:

  - Inn Occupancy: The model is highly sensitive to occupancy rates. A 10% drop in average occupancy represents a ~$35k annual revenue loss.

  - DSD Subscriber Acquisition: The model relies on consistent, month-over-month growth. Failure to achieve the “5 walk-ins per day” target and the 15% conversion rate will significantly impact high-margin, recurring revenue.

### 5. Milestones — Quarterly

| Quarter | Revenue Target | Key Operational Milestones | Owner |
| --- | --- | --- | --- |
| Q2 2026 | $81,450 | 1. Finalize and sign JP Houston programming contract.2. Achieve average Inn occupancy of 45%.3. Secure first 50 paid DSD subscribers.4. Systematize DSD walk-in sales process at Inn front desk. | JP/ChaseAmyChaseTracy |
| Q3 2026 | $123,125 | 1. Host first multi-day ticketed event in Blues Room.2. Achieve average Inn occupancy of 65% for the quarter.3. Secure first DSD Engine Tier client.4. Launch first Magazine sponsorship package. | JP/AmyAmyChaseTracy |
| Q4 2026 | $155,900 | 1. Launch Big Muddy Radio with initial sponsor packages.2. Book and execute first out-of-state tour for a managed act.3. Exceed 300 total paid DSD subscribers.4. Formalize Bearsville Creative activation plan and budget for FY27. | Elijah/ChaseJPChaseChase |
| Q1 2027 | $150,225 | 1. Achieve cash-flow positive operations on a monthly basis.2. Secure second DSD Engine Tier client.3. Finalize Big Muddy Records’ first artist signing (deal memo).4. Renew >80% of initial DSD annual subscribers. | TracyChaseJP/ChaseChase |

### 6. Action Items — Immediate Execution

Tracy Alderson-Allen: * [ ] Finalize Q2 budget in accounting software to track variance against this pro forma. * [ ] Review and approve all spend requests against budget weekly. * [ ] Establish separate bank accounts/tracking codes for Inn, Touring, and DSD revenue. * [ ] Develop standardized monthly financial reporting package for partners.

Amy Allen: * [ ] Program and confirm all Blues Room shows through July 2026. * [ ] Finalize staffing schedule for Inn front desk and bar for Q2. * [ ] Order bar inventory based on projected show attendance. * [ ] Refine breakfast service for efficiency and cost control.

Chase Pierson (Remote): * [ ] Focus sales efforts on DSD: personally contact 10 target businesses per week. * [ ] Draft and circulate Bearsville activation plan v1 for partner review. * [ ] Follow up with Studio C / Tuthill on pipeline for Q2 project work. * [ ] Provide Elijah/Miles with technical spec for Radio launch.

JP Houston (Pending): * [ ] Review and provide feedback on contract draft. * [ ] Develop a target list of 10-15 regional acts for Touring/Blues Room booking. * [ ] Outline a concept for the first multi-day event in Q3.

Contractors (Elijah/Miles): * [ ] Complete setup and testing of Icecast/OpenBroadcaster server. * [ ] Document the process for uploading and scheduling content for Big Muddy Radio. * [ ] Perform security audit of the MBT platform deployment.

### 7. Risk Register

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| 1. Slow DSD Adoption | High | High | Aggressive direct sales by Chase; offer limited-time founding member discounts; leverage Magazine content to feature early DSD members; train Inn staff on the value proposition for local businesses. | Chase |
| 2. Cash Flow Shortfall | Medium | High | Strict adherence to budget; delay non-essential capex; secure a line of credit as a backstop; accelerate sales efforts on high-margin DSD tiers. | Tracy |
| 3. Lower-than-Projected Inn Occupancy | Medium | High | Dynamic pricing implementation; targeted digital ad campaigns for key drive markets; package deals with Blues Room shows; proactive outreach to past guests. | Amy |
| 4. JP Houston Deal Fails | Low | Medium | Chase and Amy assume interim programming duties. Immediately begin search for an alternative booking agent/programmer. Maintain a strong relationship with JP as a potential future collaborator. | Chase |
| 5. Key Person Dependency | Medium | High | Cross-train responsibilities where possible (e.g., Tracy understands DSD admin, Amy understands basic finances). Document all key processes and systems. Maintain key person insurance policies. | All |

### 8. What’s De-risked vs. Aspirational

| De-Risked (Assets & Realities) | Aspirational (Targets & Hypotheses) |
| --- | --- |
| Core MBT technology platform is built and deployed. | The “$760k Lean & Mean” revenue target. |
| Big Muddy Inn is a fully-owned, operational physical asset. | The “flywheel effect” where media significantly drives hospitality bookings at scale. |
| Sanity CMS is implemented and functional. | DSD subscriber conversion rates and low churn. |
| Initial 10 articles for Magazine are published. | Monetization of Big Muddy Records and Radio within 18 months. |
| Partnership agreements with Tuthill and Studio C are in place. | Successful activation and profitability of the Bearsville node. |
| The Sprinter van for Touring is acquired and available. | Achieving consistent monthly profitability in Year 1. |
| Corporate entities (LLCs) are legally established. | The ecosystem valuation growing based on recurring tech revenue (DSD). |